## Slide 3
Slido

## Slide 5: THE JOURNEY OF TRANSFORMATION IN ACCOUNTING SYSTEM - EXPERIENCES FROM iGFMAS Salmiah Ramli
Session: 2
18 Sept 2019

## Slide 6
Portal iGFMAS
1 Year
SINCE
01.01.2018
8 Month
18 Days
Today 18-9-2019

## Slide 7: What is iGFMAS?
Upgraded
Integrated
Harmonised
Centralised
Accrual Accounting System for the Federal Government of Malaysia
iGFMAS
integrated Government Financial And Management Accounting System

## Slide 8: What is iGFMAS?
* RICEFW – Reports, Interfaces, Conversions, Extensions, Forms, Workflows
LEGACY SYSTEMS
REPLACED
7
SAP MODULES
IMPLEMENTED
14
SERVERS
CONSOLIDATED
Into a single system
37
INTERFACES
DEVELOPED
150+
RCs
19623
TRAINERS
FOR TTT
iGFMAS USERS
1000
73000
TRAINING TO HANDLE
SCOPE OF iGFMAS:
THE PROJECT TO MANAGE
300
PROJECT TEAM MEMBERS
30000
EXCEL TEMPLATES
1.3 mil
VALIDATED ASSETS
1.4 mil
PAYROLL RECORDS
1.25 b
RECORDS TO MIGRATE
1500
RICEFW FOR CUSTOMIZE
INTELLIGENT PORTAL
1000
DATA MAPPING
CASH <> ACCRUAL
8919
PROJECT & PROGRAM
ACTIVITIES
THE PROJECT HAS TO HANDLE OVER
4
EXTERNAL AGENCIES
/SYSTEMS
138

## Slide 9: Why iGFMAS?
New
Economic
Model
NEM
Bureaucratic
Reforms
Strengthening
National Policy
Formulation
Improving quality
of Human Resources
in Civil Service
Fiscal
Discipline
&
Reforms
Four Key Measures of the Financial & Reporting Reform is to implement the following initiatives:
Adopt accrual accounting for prudent fiscal
management
Strengthen expenditure control
Improve fiscal policy institutions & processes
Implement efficient broad-based tax for revenue & fiscal stability
1
2
3
4
Policy Measures For Public Sector Transformation
iGFMAS came about as a result of the decision to adopt Accrual Accounting for prudent fiscal management

## Slide 10
GFMAS
Modified Cash Basis
iGFMAS
Accrual Basis
Adoption of Accrual Accounting
01
02
03
Better financial management through complete view of government assets and liabilities
Empowering Ministries and Agencies to be financially accountable for their respective revenues and expenditures
Adds depth to the accountability and transparency of the management of public sector resources

## Slide 11
  Amendment of legislation and rules
  Liaise with AG Chambers’ for advice
Implementation Strategy
Standards &
Policies
Human
Resources
Process &
Technology
Law &
Regulation
  Setting of Accounting Policies
  IPSAS Gap Analysis
  Setting of Accounting Standards
  (MPSAS)
  Change Management
  Buy-in from all relevant parties
  Involvement of all personnel
  in the Public Sector accounting
  service.
  Human Capital Development
  Develop accounting system
  System Gap Analysis.
  Fully integrated with OBB and
  other relevant systems.
Notes: There were more than 1,500 RICEFW * where 557 programs were developed for 23 sub-modules consisting of 355 processes and 978 reports

## Slide 12: The Journey
Gap Fit Analysis
VM Lab
Procurement Process
2016-2017
2014
2012
2015
2018
2013
2019
Deferred Go Live to 2016
Requirement Gathering
System Development
EOT Application
Requirement Gathering
System Development
Strategized Go Live Approach (R1 & R2)
Deferred Go Live to 2018
Expansion of scope
Go Live (R2)
Optimization
Continuous Improvement
Increase Project Ceiling
Appoint SI
Project Kick Off
Requirement Gathering
System Development
Project Evaluation by MAMPU
PwC as PMO Project
Deferred Go Live to 2017
Changed of PD & PMO
Expansion & additional scope of work
2010 - 2011
NEM Report
SRI Lab
iGFMAS Go Live (R1)
EOT Approved
Fine Tuning
Notes: 2015 evaluation by MAMPU –scope to reasons for delayed ( 2 projects igfmas & u customs)
The Findings:
1. Complexities of the projects – a big transformation
Original plan development 18 months (development of the system concurrent with the policy /dasar))
NZ took 5 years, Australia 6 years
UK 10 years
2. Scope under estimate by vendor - think accounting in Government differ fr private sector
initial project team 100 , SME or SAP related consultant difficult to get due to myGST implementation at the same time
SME in October but the contract starts in April 2013
Solution Architect in Dec 2014
3. Differ the Akta Perakaunan Akruan – the impact
Due to the short time line, JANM & Vendor agreed to emphasise the development to accrual but when differ to 1.1.2016 Dual Ledger need to be build
2016 – discussion to consider the application EOT by iA or to terminate the SI
3 times deferred the go live date
Ist --- 30 Nov 2014 (fr 1.1.15 to 1.1.16) impact Cash Based FS has to be tabled to the Parliament – dual ledger
Tangguh pembentangan undang berkaitan di Parliament – impact go live to 2016
Maintenance of espkb & gfmas to continue – Teliti under receivableship. Can’t continue. Lantik iA
2nd --- KSP letter 2015 ( fr 1.1.2016 – 1.1.2017) fo ensure the readiness & completeness as well as the stability (mantap) of the system

## Slide 13
iGFMAS Challenges
    System slow performance
Change management
    User familiarisation
    Centralised Server & Database
    Dual Transaction & Reporting
    Adaptation Of Accrual Accounting
NEW SYSTEM REQUIREMENT
NEW REGULATIONS
PROJECT GOVERNANCE
HUMAN RESOURCES
DOCUMENTATION
SYSTEM
IMPLEMENTATION
1
2
3
4
5
6
7
    Scarce resources
    Maintaining talent
    Massive system and operational documentation
    Tight timeframe
    Concurrent policy & system development
    Massive and evolving new requirements
    Long procurement process
    Multiple layer of governance
    Amendment of Act, Rules
    and Regulations
SYSTEM DEVELOPMENT

## Slide 14
Lessons Learnt
Firm And Complete Business Requirements Before System Development Start
Feasibility Study & Findings From Operational, Policy Maker View
5
7
2
1
Identify And Maintain The Right Talent To Carry Out System Development
Rigorous Sharing Of Knowledge Between The Project Team
Realistic Timeline
Minimum Customization
3
4
6
Establish Comprehensive SOP before system Go Live
Enhance Coordination & Teamwork
8
Improve Communication
9
Notes: Involvement of SME too late – MPSAS & Government Accounting

## Slide 15
Way Forward
Continuous Improvements
Enhancing Knowledge
Complete Documentation
Data Migration Transition Period
Transfer Of Technology
5
4
3
2
1
6
Leveraging System Function
Implementation of BSP/ISP 2019-2023
7

## Slide 17
Slido